## Roadmap
Priority | Action | Goal/KPI | Effort/time estimate | Status | Responsible
P0 | Approve strategy (Tasks 1-5) and verified fact ledger | Signed go-ahead to build/publish | 0.5 day | Waiting for information | Sabaş Home owner
P0 | Confirm imprint particulars (legal name, tax office/no., MERSIS, director) | Legally compliant Imprint/Privacy (TR/EU) | 0.5 day | Waiting for information | Sabaş Home + legal
P0 | Confirm store opening hours + any prices/warranty/return/delivery terms to show | Accurate, non-fabricated on-page facts | 0.5 day | Waiting for information | Sabaş Home
P0 | Deploy new multilingual homepage (RU/EN/TR/DE) to sabashome.com | Live premium site; bounce down, dwell up | 1-2 days | Immediately implementable | Web/host
P0 | Host the AI proxy (server/ai-proxy.mjs) with the key server-side; rotate the shared key | Working grounded assistant; secret not exposed | 0.5 day | Immediately implementable | Web/host
P1 | Optimise all 5 Google Business Profiles (photos, hours, attributes, RU/EN/DE posts) | Higher Maps rank for 'mobilya/beyaz eşya/halı Alanya' | 2-3 days | Immediately implementable | Marketing
P1 | Build first reviews for the new Alaiye listing; QR-at-handover + WhatsApp follow-up | Grow real reviews across all 5 stores | Ongoing | Immediately implementable | Store teams
P1 | Replace any interim visuals with real store/product photography | Authentic, higher-trust imagery | 1-2 weeks | Immediately implementable | Marketing
P1 | Verify + publish exact Google review counts via Places API | Trust numbers shown truthfully with counts | 0.5 day | Waiting for information | Web
P2 | Add crawlable per-language URLs (/ru /en /tr /de) + hreflang | True multilingual SEO indexing | 3-5 days | Immediately implementable | Web/SEO
P2 | Add IKEA/JYSK-style 'shop by room' entry on evdego.com + sabashome.com | Room-first browsing (gap vs all local rivals) | 1-2 weeks | Immediately implementable | Web
P2 | Design turnkey packages (Furnish-a-rental, New-home starter) + B2B/hospitality track | Cross-sell bundles competitors don't show | 1 week | Waiting for information | Owner + Sales
P2 | Standardise CI (logo, colours, fonts) across signage, social grid, PDFs | Consistent premium brand identity | 1-2 weeks | Immediately implementable | Design
P2 | Localise Imprint/Privacy + assistant disclaimers into TR/RU/EN/DE (final legal text) | Compliant, trusted legal pages | 2-3 days | Waiting for information | Legal + Web
P2 | Instrument analytics (privacy-friendly) + track WhatsApp click + assistant use | Measure conversion & language mix | 0.5 day | Immediately implementable | Web
P3 | Add real product/room 3D or photography to the material showcase over time | Deeper 'wow' with real inventory | Ongoing | Waiting for information | Marketing
P3 | Publish RU/DE social content aligned to expat/second-home audience | Reach largest foreign-resident segments | Ongoing | Immediately implementable | Marketing